## Foxton Parish Council
Foxton Parish Council - s106 projects tracker
Applicant | Proposal | Amount requested | Eligible | Category | FPC recommendation | Current status | s106 allocated | Next steps | Comments
Cambridge and District Amateur Radio Club | Radio antenna/flagpole | £4,915 - £4,145 | No | N/A | N/A | Closed |  |  | Failed to meet eligibility criteria
Catherine Cairns | Dovecote meadow wildflowers | 600 | Yes | Public Open Space | Approved in principle | Complete | Nil |  | £834 Zero Carbon Grant received December 2020. No s106 funds required.
Foxton Bowls Club (1) | Replacement clubhouse | 46822 | Yes | Public Open Space | Not approved | Closed |  |  | Cost determined to be prohibitive. After discussion with the Tennis Club, both parties have decided not to pursue a joint application.
Foxton Bowls Club (2) | a) New green mower – Model LM56 Baroness b) Green levelling at end of season by Progreen c) Storage shed with base to replace existing d) Maintenance work to clubhouse e) Redecorate existing dugouts | 15186 | Yes | Public Open Space | Approved | Complete | 7500 |  | Funds to be used solely on one or more of the items listed a) to e). This grant must be used within the next 12 months.
Foxton Cricket Club (1) | Permanent cricket nets | £20-25,000 | Yes | Public Open Space | Not approved | Closed |  |  | A permanent double net would demand too much space, to the detriment of other facilities.
Foxton Cricket Club (2) | Replacement outfield mower | Up to £4,000 | Yes | Public Open Space | Pending | Open |  | To be considered by FPC
Foxton Football Club (1) | Irrigation system | £8,500 - £11,500 | Yes | Public Open Space | Not approved | Closed |  |  | Refused on environmental grounds
Foxton Football Club (2) | Two fully mobile goals | £2,100 | Yes | Public Open Space | Pending | Complete | 2100 |  | FFC contributed 50%. On condition that one of the exisiting goals is donated to FPC for recreational use.
Foxton Football Club (3) | Leaf collector | £1,157 | Yes | Public Open Space | Pending | Open | 1157 |  | Agreed but not yet paid
Foxton Parish Council (1) | Recreation Ground/churchyard hedging, three shade trees, picnic tables and wheelchair accessible path | 6887 | Yes | Public Open Space | Approved | Complete | 3443 |  | 50% funded by RGT
Foxton Parish Council (2) | Ecological and habitat improvement on Illingworth Way edge of Recreation Ground | TBA | Yes | Public Open Space | Pending | Open |  | Awaits holistic review of Recreation Ground facilities
Foxton Parish Council (3) | New play equipment incorporating bike trail on basketball court | £90,000 | Yes | Public Open Space | Pending | Open | 90000 | Consideration of feedback on design proposals. | £90,000 ring fenced for play area redevelopment; FPC will be seeking grants to help pay for this project; £3,750 paid to Jupiter Play for designs
Foxton Parish Council (4) | Re-seeding of Recreation Ground | Approx £2,000 | Yes | Public Open Space | Approved | Complete | 2600
Foxton Parish Council (5) | Purchase of recreational football goal | 150 | Yes | Public Open Space | Approved | Complete | 150
Foxton Parish Council (6) | Verti-draining of training area on RecreationGround | 125 | Yes | Public Open Space | Approved | Complete | 125
Foxton Parish Council (7) | Village information panel | TBC (c £2,000) | Yes | Public Art | Pending | Open |  | Brief to be prepared; location to be determined
Foxton Scarcrow Festival | Advertising boards | Approx £350 | Yes | Public Art | Approved | Complete | 372
Foxton Tennis Club (1) | Resurfacing of courts; replacement fencing; replacement paving | Up to £25,000 | Yes | Public Open Space | Approved | Open | 15000 | Tennis Club to advise PC of grant funds | Tennis Club is contributing at least £17k to this project. FPC agreed s106 contribution 11-01-21.
Foxton Tennis Club (2) | Shared clubhouse with Foxton Bowls Club |  | Yes | Public Open Space | N/A | Closed |  |  | After discussion with the Bowls Club, both parties have decided not to pursue a joint application.
Foxton Village Hall | Extension to main hall store | £20-25,000 | Yes | Indoor Meeting Space | Pending | Open |  | Holistic review of village hall storage; architect to be commissioned
Foxton Village Hall (2) | Installation of WiFi network | Approx £500 | Yes | Indoor Meeting Space | Pending | Open |  | Broadband connection; installation of network
Friends of the Dovecote (1) | Dovecote meadow - New interpretive display panel | 1955 | Yes | Public Art | Approved | Complete | 1955 |  | Installed January 2021
Friends of the Dovecote (2) | Re-thatching of dovecote | 2500 | Yes | Dovecote | Approved | Complete | 2500
Friends of the Dovecote (3) | New dovecote meadow gate and gatepost | 776 | Yes | Dovecote | Approved | Complete | 776
Future Foxton | Relocation of play area; new play equipment; multipurpose shelter and seating area; serving hatch from VH kitchen; wildlife garden | £106,700 - £128,500 (indicative) | Yes | Public Open Space and Indoor Meeting Space | Not approved | Closed |  |  | FPC decided not to move play area but will incorporate other elements of FF proposal in play area and recreation ground improvements
St Laurence's Church | Surveying churchyard extension | 10000 | No | N/A | N/A | Closed |  |  | Failed to meet eligibility criteria
Updated 26 October 2021